## Slide 1: Compliance Plan Update Reporting for May and June 2022
Quality Committee
26 July 2022

## Slide 2
Summary
  The Compliance Plan follows the same format as the Integrated Quality Improvement Plan (IQIP) to ensure the reporting style and transparency of progress is not lost. All actions have been aligned with the relevant Trust Strategic Objectives and include completion dates agreed with action owners. As with the exiting IQIP, any actions linked with the five Trust Quality Improvement Plans are clearly identifiable within the Compliance Plan to support transparency of monitoring, whilst avoiding duplication.
The Quality Committee is asked to note:
The 2022/23 Compliance Plan position as of Month 03
3 Actions moving to ‘At Risk’
  Following the launch of the 2022/23 Compliance Plan in April 2022 this report details the progress against the actions during May and June 2022.
  The Compliance Plan incorporates the remaining ‘open’ Must and Should Do actions from the 2021/22 IQIP with the 13 new Must and Should Do actions from the latest CQC Report and became live in April 2022. In turn, CQC actions are linked, where relevant, to the Radiology, Ophthalmology, Maternity, Urgent and Emergency Care and Elective Recovery Improvement Plans.
  All 35 actions within the 2022/23 Compliance Plan have deadlines built into the Forward Plan and include a RAG status and narrative update by exception.
  There were no actions due to be submitted to the Evidence Assurance Group in May.
  In June, 1 action from Clinical Support Services was presented to the Evidence Assurance Group, in line with the Forward Planner. This action was approved increasing the total number of actions closed to 7 (20%).
  As of June 2022, 3 actions were moved to ‘At Risk’ which relate to the Emergency Department (ED) 4hr standard and staffing levels within Radiology. See slide 7 for further details. There are no actions Behind Plan.

## Slide 3
  The tables below reflect the actions captured within the 2022/23 Compliance Plan, with 28 open actions covering Must and Should Do actions which are structured accordingly.
Overall Plan Position

## Slide 4
Overall Plan Status
Of the 35 total planned actions within the Compliance Plan, 7 actions have been closed including the 4 Section 31 conditions which remain on the Trust’s Certificate of Registration
3 actions are currently RAG rated ‘At Risk’ and no actions are behind plan at Month 04
10 Must Do actions are incorporated within the 2022/23 Compliance Plan and all remain open
3 Must Do actions are currently RAG rated ‘At Risk’
21 Should Do actions are incorporated within the 2022/23 Compliance Plan
3 Should Do actions have been closed to date, including 1 Should Do action from Clinical Support Services which was approved at the Evidence Assurance Group in June
All CQC Conditions and Warning Notices have been closed internally by the Trust
The Trust has 4 Section 31 Conditions on its Certificate of Registration
A more detailed review of the Section 31 Condition evidence for significant findings is being carried out which will inform the timing of the Trust's application to the CQC to formally request the lifting of the 2 remaining Radiology Section 31 Conditions in addition to the Maternity Condition

## Slide 5
Forward plan for the completion of actions
This table details a breakdown of all 35 actions within the Compliance Plan which are included within the forward plan.

## Slide 6
At Risk Actions
ID Ref | Category | Action Description | Owner | End Date | RAG Status
102 | Must | The trust must ensure that staffing levels are adequate to provide safe care and treatment to patients in a timely way. (Diagnostic Imaging) | General Manager CSS | 31/07/2022 | A
103 | Must | The trust must be assured that the out of hours staffing arrangement is sustainable and robust to provide safe care and treatment to patients. (Diagnostic Imaging) | General Manager CSS | 31/07/2022 | A
102 & 103 – Staffing
Due to a number of vacancies within the current establishment and a national shortage of Radiographers the service is heavily reliant on agency and bank staffing which at times puts staffing levels at risk to provide safe care and treatment. This is not a robust and sustainable arrangement at present. The service is currently undergoing a skill mix review and supporting the recruitment of apprentices and Assistant Practitioners. A consultation is planned to review the out of hours staffing provision in due course.
109 – 4 Hour ED Standard
Due to the increasing demand within the Emergency Department; there is a risk that this action is not being sustained with the 15 minute national target. The mitigating actions are that a trial is commencing that the GP stream service will work alongside the triage nurse to assess the patients within the target time however due to current recruiting concerns this target is not being met. There is a plan for a triage nurse to be placed within minor injuries to take all minor patients through the pathway.
109 | Must | The trust must improve its performance times in relation to ambulance turnaround delays, four-hour target, patients waiting more than four hours from the decision to admit until being admitted and monthly median total time in A&E. (Urgent & Emergency Care) | Deputy Medical Director | 31/03/2023 | A

## Slide 7
Actions Approved at EAG in June 2022
ID Ref | Category | Action Description | Owner | End Date | RAG Status
105 | Should | The trust should continue to embed the governance and risk management processes. (Diagnostic Imaging) | General Manager CSS | 30/06/2022 | B
No actions were due for closure in May 2022 in line with the forward planner

## Slide 8
Actions to be submitted to the EAG in July 2022
ID Ref | Category | Action Description | Owner | End Date | RAG Status
102 | Must | The trust must ensure that staffing levels are adequate to provide safe care and treatment to patients in a timely way. (Diagnostic Imaging) | General Manager CSS | 31/07/2022 | A
103 | Must | The trust must be assured that the out of hours staffing arrangement is sustainable and robust to provide safe care and treatment to patients. (Diagnostic Imaging) | General Manager CSS | 31/07/2022 | A