## Slide 1: Compliance Plan Update Reporting for July and August 2022
Quality Committee
27 September 2022

## Slide 2
Overall Plan Summary
  This report summarises the progress against the 2022/23 Compliance Plan since its launch in April 2022.
  The Compliance Plan incorporates the remaining ‘open’ Must and Should Do actions from the 2021/22 IQIP with the 13 new Must and Should Do actions from the latest CQC Report. In turn, CQC actions are linked, where relevant, to the Radiology, Ophthalmology, Maternity, Urgent and Emergency Care and Elective Recovery Improvement Plans.
  All 35 actions within the 2022/23 Compliance Plan have deadlines built into the Forward Plan and include a RAG status and narrative update by exception.
  In July, 2 actions from Clinical Support Services were presented to the Evidence Assurance Group, in line with the Forward Planner. Both actions were approved increasing the total number of actions closed to 9 (26%). No actions were due for closure in August.
  As of August 2022, there are 4 actions ‘At Risk’ which relate to the Emergency Department (ED) 4hr standard, Dedicated Pharmacy Support within Critical Care and Mandatory Training and Appraisal Rates within Maternity Services. See slide 6 for further details.
  There are no actions ‘Behind Plan’.
All actions within the Compliance Plan have been aligned with the relevant Trust Strategic Objectives and include completion dates agreed with action owners. Any actions linked with the five Trust Quality Improvement Plans are clearly identifiable within the Compliance Plan to support transparency of monitoring, whilst avoiding duplication.
The Quality Committee is asked to note:
The 2022/23 Compliance Plan position as of Month 05
4 Actions moving to ‘At Risk’

## Slide 3
  The tables below reflect the actions captured within the 2022/23 Compliance Plan, with 26 open actions covering Must and Should Do actions which are structured accordingly.
Overall Plan Position
Status | Must | Should | Section 31 | Total
Completed & Signed Off | 2 | 3 | 4 | 9
Clinical Support Services | 2 | 2 | 2 | 6
Corporate |  |  |  | 
Medicine |  |  | 1 | 1
Surgery |  |  |  | 
Women & Children |  | 1 | 1 | 2
Not Completed | 8 | 18 |  | 26
Clinical Support Services |  | 3 |  | 3
Corporate | 2 |  |  | 2
Medicine | 5 | 13 |  | 18
Surgery |  | 2 |  | 2
Women & Children | 1 |  |  | 1
Total | 10 | 21 | 4 | 35

## Slide 4
Overall Plan Status
Of the 35 total planned actions within the Compliance Plan, 9 actions have been closed including the 4 Section 31 conditions which remain on the Trust’s Certificate of Registration
4 actions are currently RAG rated ‘At Risk’ and no actions are behind plan at Month 05
All CQC Conditions and Warning Notices have been closed internally by the Trust
The Trust has 4 Section 31 Conditions on its Certificate of Registration
A decision has been made not to submit a formal application in August to request the lifting of 3 of the remaining Section 31 Conditions relating to Maternity Services and Diagnostic Imaging. Full details are included within the Section and Warning Notice Update .
It is important to note that there has been no breach of these conditions.
10 Must Do actions are incorporated within the 2022/23 Compliance Plan.
2 Must Do actions were closed at the Evidence Assurance Group in July
21 Should Do actions are incorporated within the 2022/23 Compliance Plan
3 Should Do actions have been closed to date

## Slide 5
Forward plan for the completion of actions
This table details a breakdown of all 35 actions within the Compliance Plan which are included within the forward plan.

## Slide 6
ID Ref | Service | Category | Action Description | End Date | RAG Status
101 | Surgery | Should | The service should ensure there is a dedicated pharmacist to support the service. (Critical Care) | 31/10/2022 | A
109 | Medicine | Must | The trust must improve its performance times in relation to ambulance turnaround delays, four-hour target, patients waiting more than four hours from the decision to admit until being admitted and monthly median total time in A&E. (Urgent & Emergency Care) | 31/03/2023 | A
124 | Women and Children | Must | The trust must monitor medical staff training rates, and improve appraisal rates to meet the trust target. (Maternity) | 30/11/2022 | A
130 | Corporate | Must | The trust must ensure that staff receive an annual appraisal. (Trust Overall) | 31/12/2022 | A
Actions At Risk at the end of August 2022
101 – Pharmacy Support (Critical Care)
Support from Pharmacy is infrequent, with inconsistent presence on the daily ward rounds. This is a consequence of the current high vacancy rate of Clinical Pharmacists which is a significant risk on the Trust’s Risk Register. Critical Care continues to contact pharmacy when advice is needed. The Division of Surgery also have this specific risk on their risk register and monitored by their Divisional Board.
109 – 4 Hour ED Standard (Urgent and Emergency Care)
Due to the ongoing demand on Urgent and Emergency Care at both a system and Trust level, there is a risk this action with not be achieved within the agreed timeframe. Work to improve performance against this standard forms both system working and actions within the Trust’s Urgent and Emergency Care Improvement Plan.
124 – Mandatory Training and Appraisals (Maternity)
Mandatory training and appraisal rates are monitored monthly at both Divisional and a Corporate level. All four Divisions have developed a mandatory training trajectory aiming to achieve the required compliance standard. W&C have a highlighted a risk of not achieving the 90% mandatory training compliance for CNST due to Maternity staffing vacancies, the details of which are captured on their Divisional Risk Register. Appraisals are being arranged by Line Managers, with dedicated time given to staff. Appraisals are monitored and escalated by the PDM/ PDN teams. The Division are ensuring that all of those who manage staff are trained in undertaking appraisals. Trust Mandatory Training compliance at the end of July had deteriorated slightly to 75%.
130 – Appraisals (Trustwide)
Due to the Division of W&C moving their appraisal action to ‘At Risk’ the Corporate Trustwide action cannot be closed until all Divisional actions have been completed which relate to appraisal compliance. Trust Appraisal compliance at the end July had improved slightly to 75%.

## Slide 7
Actions submitted and approved at EAG in July and August 2022
ID Ref | Service | Category | Action Description | End Date | RAG Status
102 | Clinical Support Services | Must | The trust must ensure that staffing levels are adequate to provide safe care and treatment to patients in a timely way. (Diagnostic Imaging) | 31/07/2022 | B
103 | Clinical Support Services | Must | The trust must be assured that the out of hours staffing arrangement is sustainable and robust to provide safe care and treatment to patients. (Diagnostic Imaging) | 31/07/2022 | B
To date all actions have been submitted to EAG and approved for closure within timeframes in line with the forward planner.

## Slide 8
Actions to be submitted to the EAG in the next 3 months
ID Ref | Service | Category | Action Description | End Date | RAG Status
101 | Surgery | Should | The service should ensure there is a dedicated pharmacist to support the service. (Critical Care) | 31/10/2022 | A
106 | Medicine | Must | The trust must ensure daily and weekly checks on resuscitation equipment is maintained in line with trust guidance. (Medicine) | 30/09/2022 | G
107 | Medicine | Must | The trust must ensure medicines are stored and managed appropriately. (Medicine) | 30/09/2022 | G
118 | Clinical Support Services | Should | The trust should develop a formalised vision and strategy in radiology. (Diagnostic Imaging) | 31/10/2022 | G
122 | Surgery | Should | The service should ensure that doctors mandatory training compliance is in line with the trust targets. (Critical Care) | 31/10/2022 | G
123 | Clinical Support Services | Should | The trust should ensure that staff are up to date with mandatory training. (Diagnostic Imaging) | 31/10/2022 | G
124 | Women and Children | Must | The trust must monitor medical staff training rates, and improve appraisal rates to meet the trust target. (Maternity) | 30/11/2022 | A
125 | Medicine | Should | The service should ensure that nursing appraisal rates are in line with trust targets. (Medicine) | 31/10/2022 | G
126 | Medicine | Should | The service should ensure mandatory and safeguarding training amongst medical staff is completed in line with trust targets. (Medicine) | 31/10/2022 | G
127 | Medicine | Should | The service should ensure that nursing appraisal rates are in line with trust targets. (Urgent & Emergency Care) | 30/11/2022 | G
128 | Medicine | Should | The service should ensure that all staff complete safeguarding adults and children’s’ training. (Urgent & Emergency Care) | 30/11/2022 | G
129 | Medicine | Should | The service should ensure all medical staff complete appropriate levels of safeguarding training for adults and children. (Urgent & Emergency Care) | 30/11/2022 | G