## Slide 1: Integrated Quality Improvement Plan Programme Update Reporting for February 2022
Quality Committee
29 March 2022

## Slide 2
Summary
Following publication of the CQC Inspection findings in February 2022, the Trust’s Integrated Quality Improvement Plan (IQIP) will now evolve, moving Must and Should Do actions into a single Compliance Plan aligned to the Trust’s 2022/23 Trust priorities and key Quality Improvement Plans. This will allow the organisation to build on the improvements recognised within the CQC report and inform the Trust’s own ‘journey of improvement’, underpinned by leadership and culture programmes, quality improvement, transformation and compliance. The details of the Compliance Plan and supporting governance arrangements can be found under a separate Quality Committee agenda item.
  This report notes the findings from the Clinical Review undertaken on 17th February 2022 with 2 clinical areas reviewed; Radiology and Necton Ward.
The Quality Committee is asked to note:
Progress at Month 11
The impact of the significant operational pressures on action progress
Development of the Compliance Plan
Clinical Review Findings from February 2022
  The following slides display the progress of the 2021/22 IQIP against deadlines built into the IQIP’s Forward Plan and include a RAG status and narrative update by exception. Note this is the last progress report against the existing 2021/22 IQIP which comprises of 83 actions, prior to its transition to a 2022/23 Compliance Plan.
  To date, 55 (66%) of the 2021/22 IQIP actions have been approved for closure as of Month 11.
  In February, 3 actions were submitted for closure to the Evidence Assurance Group (EAG):
    1 action was approved
    2 actions were declined
  6 schemes (23 Actions) are ‘Behind Plan’. All 23 open actions will be incorporated into the 2022/23 Compliance Plan to ensure these are completed and evidence of assurance supports the closure of these actions. It is important to note that 9 of 12 mandatory training related actions that make up one 1 scheme have been approved for closure. However these actions can only be closed when the EAG is assured of improvement against the whole scheme.
  Whilst deadlines for all actions were agreed in March 2021, a more detailed review as part of the improvement work during 2021 identified more complex and deep-rooted issues in a number of schemes. In turn, unrelenting operational pressures as a result of the COVID-19 pandemic across the Norfolk & Waveney system and the National Level 4 incident being declared in December, also impacted on the delivery of a number of actions against recovery timeframes. This will be monitored closely over the coming months, particularly in relation to mandatory training and appraisal compliance

## Slide 3
  The table below reflects the 83 actions captured within the 2021/22 IQIP, with 28 open actions covering Must and Should Do actions which are structured accordingly.
Overall Programme Position

## Slide 4
  Of the remaining 28 open actions, 22 have been categorised as ‘Corporate’ actions as these relate to all four Divisions and or, all Trust staff.
Corporate Action Themes

## Slide 5
Overall Programme Status
Of the 83 total planned actions within the IQIP, 55 have been completed
1 action was approved in February 2022
2 actions were declined in February 2022
2 Must Do actions were declined in February 2022
1 Should Do action was approved in February 2022
The CQC noted improvements against all Should Do actions were noted in the services inspected.
As of January 2022, all CQC Conditions and Warning Notices have been closed internally by the Trust
4 Section 31 Conditions remain on the Trusts Certificate of Registration
Following the most recent inspection, the CQC confirmed closure of the 16 remaining 29A Warning Notice Conditions.
The Trust has 4 Section 31 Conditions on its Certificate of Registration. The Trust will apply for the lifting of 3 of the remaining 4 conditions in March.

## Slide 6
Forward plan for the completion of actions
This table details a breakdown of all 83 actions within the IQIP which are included within the Forward Plan.

## Slide 7
RAG Rated Programme Position as of February 2022
The following sets out the overall programme position.
23 actions rated as ‘Behind Plan’ and recovery actions have been agreed.

## Slide 8
Actions Approved at the EAG in February 2022
1 action were approved at EAG in February 2022
ID Ref | Service | Category | Action Description | Owner | End Date | RAG Status
007 | Corporate | Should | The trust should ensure that waiting times from referral to achievement of preferred place of care and death are timely. | Chief Nurse | 22/02/2022 | B

## Slide 9
Actions Declined at the EAG in February 2022
2 actions were declined at EAG in February 2022
ID Ref | Service | Category | Action Description | Owner | End Date | RAG Status
057 | Clinical Support Services | Must | The trust must ensure that staffing levels are adequate to provide safe care and treatment to patients in a timely way. | DLT Clinical Support Services | 22/02/2022 | R
058 | Clinical Support Services | Must | The trust must be assured that the out of hours staffing arrangement is sustainable and robust to provide safe care and treatment to patients. | DLT Clinical Support Services | 22/02//2022 | R
057 – 058 Clinical Support Services
The EAG noted the improvements made relating to these actions, however requested additional evidence on fill rates and the process for safe staffing, RTT and Backlog data. These actions have also been incorporated in the Radiology Improvement Plan and monitored through the supporting governance arrangements.
These actions will be incorporated into the Compliance Plan

## Slide 10
Actions Behind Plan at the end of February 2022
015 National and Local Audit Targets
This scheme (3 actions) forms part of the wider Clinical Audit Improvement Plan. Some actions have evolved following the application of the PDSA methodology; as a result, they are currently ongoing. A revised submission date has been agreed for April 2022.
These actions will be incorporated into the Compliance Plan
017 Appraisal Rates
Although significant progress has been made Appraisals remain off trajectory and target as full capacity protocols continue to delay appraisals. Appraisals were cancelled due to managers being included within the staffing numbers and sickness of staff. All areas have been asked to reschedule appraisals and complete trajectories for completing appraisals. HR will continue to monitor appraisal compliance rates to ensure these are completed in line with the Trust target. This action remains ‘Behind Plan’
These actions will be incorporated into the Compliance Plan
ID Ref | Service | Category | Action Description | Owner | End Date | RAG Status
015 | Corporate | Should | The service should ensure that performance in national and local audits is in line with targets. (UEC) | Director of Patient Safety | 31/10/2021 | R
015 | Corporate | Should | The service should ensure that performance in national and local audits is in line with targets. (Med) | Director of Patient Safety | 31/10/2021 | R
015 | Corporate | Should | The trust should ensure that compliance with national and local audits is in line with targets (EOL) | Director of Patient Safety | 31/10/2021 | R
017 | Corporate | Must | The trust must monitor medical staff training rates, and improve appraisal rates to meet the trust target. | Director of People | 30/11/2021 | R
017 | Corporate | Must | The trust must ensure that staff receive an annual appraisal. | Director of People | 30/11/2021 | R
017 | Corporate | Should | The service should ensure that nursing appraisal rates are in line with trust targets. | Director of People | 30/11/2021 | R
017 | Corporate | Should | The service should ensure that nursing appraisal rates are in line with trust targets. | Director of People | 30/11/2021 | R

## Slide 11
Actions Behind Plan at the end of February 2022
018 Mandatory Training Rates
9 individual actions were approved at Novembers EAG, but 3 were declined. As all 12 actions form one overarching scheme, this can only be approved for closure when the EAG is assured of improvement against all 12 actions. Due to the current Level 4 Incident across the NHS and unprecedented pressures within the Norfolk and Waveney system, high sickness and training temporarily suspended these actions remains ‘Behind Plan’ with a further revised submission date of May.
The remaining three actions will be incorporated into the Compliance Plan
ID Ref | Service | Category | Action Description | Owner | End Date | RAG Status
018 | Corporate | Must | The trust must review the knowledge, competency and skills of staff in relation to the Mental Capacity Act and Deprivation of Liberty safeguards | Director of People | 30/09/2021 | R
018 | Corporate | Should | The service should ensure that all staff complete safeguarding adults and children’s’ training. (Emergency Department) | Director of People | 30/09/2021 | R
018 | Corporate | Should | The trust should ensure that staff are up to date with mandatory training. (Diagnostic Imaging) | Director of People | 30/09/2021 | R
018 | Corporate | Must | The trust must ensure that mandatory training attendance, including training on infection prevention and control and safeguarding of vulnerable children and adults, improves to ensure that all staff are aware of current practices and are trained to the appropriate level. | Director of People | 30/09/2021 | B
018 | Corporate | Should | The trust should ensure that mandatory training compliance meets the trust target for all staff groups. | Director of People | 30/09/2021 | B
018 | Corporate | Should | The service should ensure that all staff complete mandatory training in key skills. | Director of People | 30/09/2021 | B
018 | Corporate | Should | The service should ensure that staff have completed the relevant life support training for their clinical roles. | Director of People | 30/09/2021 | B
018 | Corporate | Should | The trust should ensure staffs mandatory and safeguarding training compliance meets the trust target. | Director of People | 30/09/2021 | B
018 | Corporate | Should | The service should ensure that staff complete mandatory training. | Director of People | 30/09/2021 | B
018 | Corporate | Should | The service should improve medical staff compliance with safeguarding training. | Director of People | 30/09/2021 | B
018 | Corporate | Should | The service should ensure that all staff complete mandatory training to improve compliance in line with the trust target. | Director of People | 30/09/2021 | B
018 | Corporate | Should | The service should ensure that safeguarding adults and children’s training compliance is in line with the trust target. | Director of People | 30/09/2021 | B

## Slide 12
Actions Behind Plan at the end of February 2022
ID Ref | Service | Category | Action Description | Owner | End Date | RAG Status
055 | Medicine | Must | The trust must improve its performance times in relation to ambulance turnaround delays, four-hour target, patients waiting more than four hours from the decision to admit until being admitted and monthly median total time in A&E. | Chief Operating Officer | 31/10/2021 | R
055 | Medicine | Should | The service should ensure that care and treatment are accessible at the time of need and referral to treatment times and waiting times are in line with national standards. | Chief Operating Officer | 31/10/2021 | R
057 | Clinical Support Services | Must | The trust must ensure that staffing levels are adequate to provide safe care and treatment to patients in a timely way. | DLT Clinical Support Services | 31/01/2022 | R
058 | Clinical Support Services | Must | The trust must be assured that the out of hours staffing arrangement is sustainable and robust to provide safe care and treatment to patients. | DLT Clinical Support Services | 31/01/2022 | R
055 Ambulance Turnaround Four Hour Target
This scheme (2 actions) formed part of the discussion with the CQC regarding the impact of COVID-19 on national performance standards and expectations regarding evidence to demonstrate this action has been addressed. The CQC confirmed they recognise the national challenges and would look at the systems and process the organisation has put in place since 2018 to safely assess and treat patients with the Emergency Department, including pathways of care, responding to increasing demand, escalation and oversight of the department. In view of this information a decision will now be made by the COO when this action will be submitted to the EAG.
057 Adequate Staffing Levels
See Slide 9
058 Out of Hours Staffing Arrangement
See Slide 9

## Slide 13
Actions to be submitted to the EAG in March 2022
1 schemes (2 actions) are due to be presented at EAG in March 2022
ID Ref | Service | Category | Action Description | Owner | End Date | RAG Status
011 | Women & Children | Should | The service should continue to work on the culture within the department. | DLT Women & Children | 30/04/2022 | G
011 | Clinical Support Services | Should | The trust should continue to improve staff engagement. | DLT Clinical Support Services | 30/04/2022 | G
ID Ref | Service | Category | Action Description | Owner | End Date | RAG Status
068 | Clinical Support Services | Should | The trust should review processes to ensure that patients are able to access diagnostic imaging services in a timely manner. | DLT Clinical Support Services | 29/03/2022 | G
069 | Clinical Support Services | Should | The trust should continue to embed the governance and risk management processes. | DLT Clinical Support Services | 29/03/2022 | G
070 | Clinical Support Services | Should | The trust should develop a formalised vision and strategy in radiology. | DLT Clinical Support Services | 29/03/2022 | G
In line with the forward planner the 3 actions below were due to be presented in March 2022, however in light of the recent CQC inspection report the IQIP has evolved into a single Compliance Plan aligned to the 2022/23 Trust priorities and key Quality Improvement Plans. All remaining open actions from the IQIP have been reviewed by each action owner and given new completion dates, therefore these actions will be presented at EAG in May 2022.

## Slide 14
Clinical Review Programme: Assurance Actions Sustained and Embedded
  The Monthly Clinical Review Programme was cancelled in December and January to ease pressures on clinical teams, the programme recommenced in February 2022.
  Clinical Review 17th February 2022
  Due to operation pressures, the Director of Patient Safety took the decision to run a scaled down Clinical Review in February. A team of five non-clinical staff were involved in this review, consisting of the Head of Clinical Effectiveness and Patient Safety, Health and Safety Manager, Personal Assistant to the Head of Midwifery & Nursing, as well as two Trust Governors.
  The review was limited to 2 areas:
  Necton Ward
  Radiology Department
  In view of the significant pressures on staff as a result of COVID-19 the KLOE focused on patient and staff experience whilst drawing on broader findings through the use of the ‘15 Steps’ methodology.
Areas of Good Practice:
Both review teams felt they had really positive visits to the areas
Both areas were welcoming and accommodating upon arrival
Staff were engaged and enthusiastic when speaking to the team
Across both areas the review teams observed positive interactions between staff and patients – Staff introduced themselves
Whilst both areas were busy, staff appeared calm and in control
Patient care was good, caring and compassionate
On both areas staff exuded a positive team attitude / spirit
Staff on both areas expressed feeling confident when speaking up and were able to articulate the method for raising concerns
Areas of Improvement:
Compliance with Information Governance standards appeared to be an issue on Necton Ward, with computer screens and notes trolleys left unlocked when unattended
During the review of the Radiology Department, staff raised concerns regarding the implementation of the new Radiology Information System which had been problematic but informed the review team that managers were aware and issues were being addressed.
On the day of the review, both areas faced challenges with staffing levels (Due to sickness), but staffing was safe with mitigations in place

## Slide 15
Clinical Review Programme: Assurance Actions Sustained and Embedded
  Necton Ward
  Good Practice:
  It was apparent that staff knew their roles and responsibilities
  The ward felt well-ventilated, de-cluttered and clean
  It was apparent that staff were actively supporting one another
  Call-bells and telephone calls were answered promptly
  Discharge planning was good with discharge plans in place
  The team observed good multidisciplinary working
  Patients expressed feeling well-cared for and happy on the ward
  Good adherence to Infection Control Standards were observed
  Areas of Improvement:
  During the review the team identified computer screens left unlocked when unattended, leaving patient identifiable information on display.
  The review team also noted the patient notes trolley was unlocked when unattended - This was feedback to the Nurse in Charge
  Due to staffing levels, the review team noted a delay in patient transfers due to a lack of preparation
Radiology Department
Good Practice:
  The review team noted how the area had a very different feel, and highlighted how the culture programme has made a positive change to the departments dynamic
  Staff across the department were friendly and welcoming
  Overall staff across the department felt that the culture had really improved, and staff expressed feeling valued
  Staff were able to talk about the Radiology Improvement Plan
  Staff were able to articulate how learning is captured and shared
  Areas of Improvement:
  The review team notes concerns raised by staff regarding the implementation of RIS - Staff expressed how implementation has been problematic but also acknowledge issues were being addressed
  The department still faces staffing challenges, but this was acknowledged by staff and the department have plans in place to address these challenges
Overall the review teams felt they had positive visits to all wards. They observed good multidisciplinary working, which was caring and compassionate, and staff were engaged and enthusiastic to speak to the review teams. Whilst good practice was noted, the review teams did identify the specific areas for improvement for each area.

## Slide 16
Clinical Review Programme: Identified Areas for Action Update
Theme | Action Required | Action Taken
Patient Records / Locked Screens | Patient records are a recurring theme at the monthly clinical reviews . Notes trolleys are often left open / unlocked and notes are left unattended. Screens to be locked when unattended | The current trolleys for transporting records across the Trust are not all lockable. New lockable trollies have been identified and ordered. The Information Governance Lead also continues to audit wards monthly. An alert has been sent to staff to ensure patient records are always safely stored. The lock screen ‘time out’ for the Trust has been shortened to 5 minutes.
Answering Phones/Call Bells | Phones and Call Bells are not always answered in a timely manner and often left to nursing staff in the absence of the Ward Clerk | Communications shared Trustwide ‘In The Know’ reiterating the importance of answering phones as it is important that we keep our patient’s loved ones up-to-date and informed. Simply acknowledging the call bell can put a patient at ease. It is everybody’s responsibility to ensure these are responded to. Family Liaison Officers ensure relatives/carers are kept informed and support the answering of calls during visits to the inpatient wards.
Radiology Information System (RIS) | Staff advised the implementation of the new Radiology Information System (RIS) has been problematic | RIS Project Board established which meets weekly and is chaired by the Deputy CEO. Sighted on all risks and issues are being addressed and resolved through this group. Staff are being kept updated and have been involved in the development of the Radiology Improvement Plan.
Communication | Patients who were born or grew up outside the UK experiencing difficulties in understanding different parts of the NHS | New menu tablets are available within the Trust, which has pictures of the menus to aid patient choice. The Trust is using Access Migrant Support to work with the Patient Experience Team to make access to the NHS more accessible.
Staffing | Staff raising concerns about staffing levels. | Radiology department have plans in place to address these challenges, it is part of their improvement plan to fill vacancies. Wards being aware of transfers coming in to ensure delays are minimal. All areas were safe. Arrangements in place to ensure rosters are covered.
  The table below details a number of themes identified during these clinical reviews and the action taken to address these areas of concern.